## Timeline
|  | #E84A27 | #E9E9E8 | #34466B | #6E7887 | #363D44 | #F4F4F2
| RED-FLANNEL | Project Timeline
|  | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | 2021-05-09
| Team Formation | 2021-02-28: R / E / T / C
Project Initiation
| Ideation (Problem Identification) | 2021-03-07: R / E / T / C
| Literature Search | 2021-03-14: R / E / T / C
| Problem Formulation | 2021-03-14: R / E / T / C
| Success Metrics | 2021-03-21: R / E / T / C
| Analytic Infrastructure | 2021-03-21: E / C
| Data Discovery & Analysis | 2021-03-21: R / T
Project Proposal
Motivation | bar: 2021-03-28
Literature Survey | bar: 2021-03-28
Data Discovery & Analysis | bar: 2021-03-28
Approach | bar: 2021-03-28
| Experimental Setup | 2021-03-28: E / C
Timeline | bar: 2021-03-28
Project Execution
Data Gathering | bar: 2021-03-28
| Study Design | 2021-03-28: R / E / T / C
Clean & Process Data
Image Augmentation [Rotation / Filtering] | bar: 2021-04-04
Performance Testing | bar: 2021-04-04
Develop & Implement Modeling Pipeline (FLANNEL)
Adj. Basis Models w/ New CNN Models | bar: 2021-04-04
Performance Testing | bar: 2021-04-04
| Results Interpretation | 2021-04-11: R / E / T / C
Project Draft
Abstract | bar: 2021-04-18
Introduction | bar: 2021-04-18
Approach/Metrics | bar: 2021-04-18
Experimental Results | bar: 2021-04-18
| Discussion | 2021-04-18: E / T
| Conclusion/Optimization | 2021-04-18: R / C
Final Submission
| Post-Draft Optimizations / Adjustments | 2021-04-25: R / E / T / C
| Final Paper | 2021-05-02: R / T
| Presentation Deck | 2021-05-02: E / C
| Code Repository Cleanup, Documentation, Public Release | 2021-05-02: R / E / T / C
Figure. 2: Project Timeline

## F1 Tables
Table 2. Performance comparison on F1 score for standard image pre-processing
| COVID-19 | Pneumonia | Normal | Macro-F1 | Avg. Train Time (per Epoch)
Base Leaners
Inception V3 | 0.87 | 0.93 | 0.85 | 0.88 | 478 seconds
VGG19 | 0.69 | 0.84 | 0.401 | 0.65 | 6.2 seconds
ResNeXt101 | 0.97 | 0.94 | 0.98 | 0.97 | 676 seconds
Resnet152 | 0.96 | 0.98 | 0.94 | 0.96 | 428 seconds
Densenet161 | 0.97 | 0.98 | 0.95 | 0.97 | 392 seconds
Alexnet | 0.91 | 0.84 | 0.64 | 0.82 | 140 seconds
ShuffleNet* | -- | -- | -- | -- | --
MNRSNet* | -- | -- | -- | -- | --
Flexnet* | -- | -- | -- | -- | --
SqueezeNet* | -- | -- | -- | -- | --
* These base learners will be evaluated before final submission
Table 3. Performance comparison on F1 score for RED Flannel image pre-processing
| COVID-19 | Pneumonia | Normal | Macro-F1 | Avg. Train Time (per Epoch)
Base Leaners
Inception V3 | 0.87 | 0.93 | 0.85 | 0.88 | 478 seconds
VGG19* | -- | -- | -- | -- | --
ResNeXt101 | 0.96 | 0.95 | 0.98 | 0.97 | 682 seconds
Resnet152 | 0.96 | 0.98 | 0.94 | 0.96 | 428 seconds
Densenet161 | 0.97 | 0.98 | 0.95 | 0.97 | 392 seconds
Alexnet | 0.91 | 0.84 | 0.64 | 0.82 | 140 seconds
ShuffleNet* | -- | -- | -- | -- | --
MNRSNet* | -- | -- | -- | -- | --
Flexnet* | -- | -- | -- | -- | --
SqueezeNet* | -- | -- | -- | -- | --
* These base learners will be evaluated before final submission